## Slide 1: NGEnvironment
Foster European Active Citizenship and Sustainability Through Ecological Thinking by NGOs
Next steps & Meeting Evaluation
NGEnvironment 5th Partner Meeting via ZOOM The NGEnvironment Survival Guide and Policy Paper Conference
23rd- 25th of March 2021
Project Number: 2018-1-DE02-KA204-005014
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors,
and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
Welcome to our Online Meeting!
The NGEnvironment Survival Guide and Policy Paper Conference
NGEnvironment 5th Partner Meeting via ZOOM 23rd- 25th of March 2021
Project Number: 2018-1-DE02-KA204-005014

## Slide 3
The Timeline for NGEnvironment
1

Start 01 Sep'18
Intellectual Output 3:
Nov'18 - Jan'21
Intellectual Output 2: Nov'18- August‚19
Intellectual Output 1:
Sep'18 – May'19
Project Management Sep '18 – Aug 21
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
2018
2019
2020
Nov
2018
Aug 2021
Start of the project
September 2018
Intellectual Output 4:
Nov'18 - Aug'21
Intellectual Output 5:
Oct´18- Aug‘21
Jan
2021
2021
Sep
2018
Intellectual Output 6:
Dec´18- July‘21
Intellectual Output 7:
Aug´20- June‘21
Intellectual Output 8:
Aug´20- June‘21
Intellectual Output 9:
Dec´20- Aug‘21
Aug
2020

## Slide 4
Overview on the 9 Intellectual Outputs
IO 1
-
Summary research
RC
IO 2
-
Induction to Pedagogy for NGO staff
EPEK
IO 3
-
Training package for social and green NGO leadership
UPB
IO 4
-
Online platform and observatory
AL
IO 5
-
Engagement toolkit
GIE
IO 6
-
Audiovisual instructive package
FIP
IO 7
-
Survival guide for NGO Founding and Funding
PC
IO 8
-
Policy paper
SIN
IO 9
-
Laymen Report
GIE
2


Coming soon
Coming soon



ongoing


ongoing

## Slide 5
8
FIPL
  Status? Next Steps?
Creation of NGEnvironment Video Testimonial(s)
Future in Perspective has been allocated 30 research and 30 technical days for developing such tasks
The remaining partners have been allocated 10 research days and 3 technical days for reviewing and translating subtitles
IO6 - Audiovisual instructive package –
Current state and upcoming tasks

## Slide 6
9
Research will be conducted in each partner country until 31/03/2021
PC will collate information: June 2021
According to the results found, the actual guide will be designed, produced, adapted to each partner country and translated to all partners’ languages
All Partners translation: June-August 2021
IO7 - Survival guide for NGO Founding and Funding
Current status and upcoming tasks

## Slide 7
10
Permacultura Cantabria will collate information and present a final version in English at the final conference
Output will be made available as a project’s result in the website and through social media
Asociación Cultural y Medioambiental Permacultura Cantabria has been allocated 32 research and 8 technical days to prepare research framework, conduct research, collate data from the various countries and contribute to the Spanish translation
The remaining partners have been allocated 8 research days and 4 technical days to conduct research, adjust contents to country’s reality and translate contents.
IO7 - Survival guide for NGO Founding and Funding
Current status and upcoming tasks

## Slide 8
11
SINERGIE will lead the development of the Policy paper
SINERGIE will draft the policy paper based on the responses to a policy questionnaire they will develop
This questionnaire will be completed by all partners with appropriate stakeholders
The policy paper will also be informed by a series of discussions and Skype interviews with project partners and stakeholders over the lifetime of the project
A draft structure will be presented at the fifth partners meeting
The policy paper will be presented in the Final Conference.
All partners will translate the policy paper.
IO8 - Policy paper
Current status and upcoming tasks

## Slide 9
12
Across limits will design and layout the document
It will be printed in all partner languages and also available for download from the project website
SINERGIE has been allocated 30 research and 6 technical days for researching and drafting the policy paper
The remaining partners have been allocated 8 research days and 4 technical days for documental preparation and translations.
IO8 - Policy paper
Current status and upcoming tasks

## Slide 10
12
GIE will lead the realization of the report, collating and summarizing all important information produced during the project’s lifecycle and transform it into very simple accessible language
Besides exploring data of the online observatory, GIE will also conduct research on the state-of-the-art regarding the NGO sector consulting EU statistics and other official and relevant databases
Specific research needed to be done in the consortium’s countries will be supported by the partners and their working groups.
GIE has been allocated 34 research days and 12 technical days for research, document preparation, English and Romanian writings
All remaining partners have been allocated 8 research days and 4 technical days to that they can contribute to the report's content, review, validate and translate final contents to their local languages.
GIE will start working on the laymen report by month 24 and present a draft of the structure and contents to be addressed in the 5th partner meeting
Regular online meeting will occur after this meeting and the final version will be available in month 34 to be presented in the Final Conference
IO9 - Laymen report
Current status and upcoming tasks

## Slide 11
IO2:
  Creating Evaluation Research Report (if it has not yet been created)  Deadline: latest until middle of April 2021
IO3:
  Creating Evaluation Research Report (if it has not yet been created)  Deadline: latest until middle of April 2021
1
13
Summary of all current tasks

## Slide 12
IO6: Task: Creation of NGEnvironment Video Testimonial(s)
IO7: Tasks:
  Research will be conducted in each partner country in relation to the research framework by PC
  Translation of final research report in partner language
IO8: Tasks:
  SINERGIE will provide the partners with a draft policy paper
  This questionnaire will be completed by all partners with appropriate stakeholders
IO9: Tasks:
GIE will start working on the laymen report by month 24 and present a draft of the structure and contents to be addressed in the 5th partner meeting
1
14
Summary of all current tasks

## Slide 13
Multiplier Events:
  Conduct (online) Multiplier Events until July 2021
  N= 30 persons
  Presenting all IOs and results of the project
  Evidences
    Evidence of the multiplier event carried out virtually, stating the title and date of the event.
    Evidence of the number of participants by a declaration signed by the organiser stating the names of the participants and the name and address of the sending organisation or institution.
    Documents used or distributed at the multiplier event.
1
15
Summary of all current tasks

## Slide 14
General tasks:
  Send UPB the missing timesheets and material of the financial report
  Send UPB signed participation lists of Steering Committees
  Send UPB signed Declarations of Attendance of M4/ M5 via post
  Final Conference in June/ July 2021
    Leading organisation: UPB
    Information: 2 days, set of 50 local and 7 foreign representatives of the NGO sector at policy and practice levels will attend; 50 Germans, selected from UPB and 1 per each of the remaining partner countries
1
15
Summary of all current tasks

## Slide 15
Online Meeting Evaluation
1
17
Please follow the link to access the online survey:
https://umfragen.uni-paderborn.de/index.php/289487?lang=en
Please take 5 minutes to fill in the questionnaire.
The questionnaire is anonymous.
After the meeting Jana will also send you the link.

## Slide 16
Thank you very much for your attention!
Contact:
Prof. Dr. Marc Beutner
University of Paderborn
Department Business and Human Resource Education
Chair Business and Human Resource Education II
Warburger Str. 100, 33098 Paderborn
Tel: +49 (0) 52 51 / 60 - 23 67
E-Mail: marc.beutner@uni-paderborn.de
The European Commission support for the production of this publication does not constitute an endorsement of the contents which reflects the views only of the authors,
and the Commission cannot be held responsible for any use which may be made of the information contained therein.